## Sheet1
Time Before Move | Task/Event | Completed
2 years | Define business and space needs. Begin to compile costs in order to develop move budget.
2 years | Contact commercial real estate agents, developers, architects - View or create options for new space.
1.5 years | Develop move committee - meet with committee - assess needs for new interior - design/furniture.
1.5 years | Obtain/review floor plan for current space. Decide what's working and what needs to be improved.
1.5 years | Work with planner or future leasing company to develop proposal for potential new space.
1 year | Begin looking at new spaces.
6 months | Negotiate for new space.
6 months | If large move, establish teams/team leads for different aspects. (IT relocation, Office Furniture, Design, etc.)
6 months | Create risk management plan - What could go wrong and how can we prepare for it? -
Include discussion of these concerns with any vendors.
6 months | Create inventory of all office equipment, furniture, artwork, servers, PCs.
This will help you in discussions with movers and in case anything is missing after the move.
6 months | Obtain blueprint of new office space. This will help you to develop the space and be useful when ordering furniture/copiers/printers.
6 months | Determine placement of major items on your floor plan. Server room placement is critical. Decide if back-up power is needed for server.
Server Room, computers, printers (community and personal), fax machines, scanners, copiers, postal machines, shipping label machines, etc.
6 months | Create proposed furniture orientation/layout using blueprint.
6 months | Contact moving companies. Get estimates on move.
4 months | Contact furniture companies for selection and pricing of any items needed - Order furniture (some office furniture can take 16 weeks to receive).
4 months | Send memo to staff regarding critical files - Devise plan for backing up all critical files prior to move.
3 months | Confirm location of all vital electronic files - create list.
3 months | Review all "hard" files. Are all needed? Are all needed regularly?
Create list of what files can be destroyed, what can be stored off-site and what needs to move and be readily available.
3 months | Meet with IT staff or IT relocation vendor to discuss how files will be backed up. Ensure you have a back-up plan in case vital computers or servers
are harmed in the move. Have IT staff or vendor do a "test restore" to ensure it will be effective if needed after actual move.
3 months | Determine any phone needs. Contact phone vendor.
Determine exactly where voice and data lines will be installed. Be sure the phone service you currently use is available at your new location.
3 months | Conduct on-site inspection. This allows for time to correct construction issues prior to occupancy.
3 months | Hire moving company. (Check BBB rating and references)
3 months | Order carpeting
2 months | Order new computers if needed. Find local supplier (new location) for office supplies (paper, ink, pens, etc.)
2 months | Order new business cards and stationary, envelopes with new contact information for all who need them.
2 months | Finalize details for phone system and Internet service
2 months | Now that vendors have been chosen, reassess your risk management plan
2 months | Company meeting. Review details of the move and what each employee will be responsible for when the move occurs (e.g. - packing personal items).
2 months | Create master list of all vendors now that they've been chosen. Verify all contact numbers including cell phones for all sales reps.
2 months | Confirm all installation and relocation dates with all vendors to ensure everything is on schedule.
2 months | Have all phone and computer wiring installed.
2 months | Have IT department or outside IT vendor do final restore test to ensure moving protocol is effective in case of emergency.
2 months | Consider investing in back-up generator for new location. Consider cost of business interruption in case of emergency situations.
1 month | Confirm carpeting order and shipment
1 month | Meet with moving company to verify all details of the move and contact building management to reserve elevators day of move. Make sure rep of moving
company has inspected new location, if they haven't already done so. Mover should do final assessment of access to areas needed.
1 month | Confirm all installation and relocation dates will all vendors.
1 month | Make sure all employees have list of new address and phone numbers to start sharing with customers/prospects.
10 days | Ensure everything is lined up for the move date.
10 days | Have carpet installed
10 days | Send moving "agenda" to all employees. Verify current cell phone numbers for any team leaders.
7 days | Test new phone numbers/phones/Internet service at new location.
2 days | Complete all packaging and labeling. Use a number system where each area of the new location corresponds to a number. Be accurate!
2 days | Visit new location. Make sure everything is ready for the movers to do their job. Verify key employees involved with the move are prepared.
Train employees on any security procedures at new location as well as how to use new phone system (if any).
1 day | Have new computers and other machines delivered. Have employees do last minute packing. Make certain all employees know where to go after the move.
Move day | Stand back and observe movers at old and new locations.
1 day after move | Enjoy your new location!